## Project Signoff
PROJECT COMPLETION REVIEW & APPROVAL OF SUBSECTIONS
| Project Number: | [PROJECT #]
| Project Name: | [PROJECT NAME]
|  | FAIL (Initial/Date) | Rework (Initial/Date) | Comments (required if FAIL) | PASS (Initial/Date) | Final Comments (as needed)
1 | In-Process Inspections (QA In-Process Inspector) | / | / |  | /
2 | Interior non-IT Equipment IDs (Electrical Team Lead) | / | / |  | /
3 | Exterior non-IT Equipment IDs (Assembly Team Lead) | / | / |  | /
4 | Road Test (Assembly Team Lead) | / | / |  | /
5 | Water Test (Assembly Team Lead) | / | / |  | /
6 | Physical & Operational Tests (Either Team Lead) | / | / |  | /
7 | Quantitative Tests (Electrical Team Lead) | / | / |  | /
8 | Parasitic Drain Test (Electrical Team Lead) | / | / |  | /
9 | IT Equipment Tests (IT Team Lead) | / | / |  | /
10 | Final QC Inspections (QA Final Inspector) | / | / |  | /
11 | Form 107 Complete (QA Representative) | / | / |  | /

## IP Inspection FAB
Project Number: | [PROJECT #] |  | In-Process Inspection FAB
Project Name: | [PROJECT NAME]
FAB Birdcage Inspection | FAIL (Initial/Date) | Rework (Initial/Date) | Comments (required if FAIL) | PASS (Initial/Date) | Final Comments (as needed)
Subframe welds acceptable | / | / |  | /
Tongue and reinforcement welds acceptable (Trailer only) | / | / |  | /
Floor welds acceptable | / | / |  | /
AFT wall welds acceptable | / | / |  | /
CS wall welds acceptable | / | / |  | /
FWD wall welds acceptable | / | / |  | /
SS wall welds acceptable | / | / |  | /
Roof bow welds acceptable | / | / |  | /
Ceiling hanger brackets correctly located, deburred | / | / |  | /
FAB Final Inspection - Aft Wall
AFT wall skins free of surface defects | / | / |  | /
AFT wall skin gaps consistent | / | / |  | /
AFT wall trim free of defects | / | / |  | /
AFT wall trim securely bonded | / | / |  | /
AFT wall trim free of gaps between skin and trim | / | / |  | /
If cutouts are present, frames free of router damage | / | / |  | /
If cutouts are present, cutouts meet CAD requirements | / | / |  | /
If required, backers installed, correctly located | / | / |  | /
FAB Final Inspection - CS Wall
CS Wall Skins free of surface defects | / | / |  | /
CS Wall Skin gaps consistent | / | / |  | /
CS Wall Trim free of defects | / | / |  | /
CS Wall Trim securely bonded | / | / |  | /
CS Wall Trim free of gaps between skin and trim | / | / |  | /
If cutouts are present, frames free of router damage | / | / |  | /
If cutouts are present, cutouts meet CAD requirements | / | / |  | /
If required, backers installed, correctly located | / | / |  | /
FAB Final Inspection - FWD Wall
FWD Wall Skins free of surface defects | / | / |  | /
FWD Wall Skin gaps consistent | / | / |  | /
FWD Wall Trim free of defects | / | / |  | /
FWD Wall Trim securely bonded | / | / |  | /
FWD Wall Trim free of gaps between skin and trim | / | / |  | /
If cutouts are present, frames free of router damage | / | / |  | /
If cutouts are present, cutouts meet CAD requirements | / | / |  | /
If required, backers installed, correctly located | / | / |  | /
FAB Final Inspection - SS Wall | FAIL (Initial/Date) | Rework (Initial/Date) | Comments (required if FAIL) | PASS (Initial/Date) | Final Comments (as needed)
SS Wall Skins free of surface defects | / | / |  | /
SS Wall Skin gaps consistent | / | / |  | /
SS Wall Trim free of defects | / | / |  | /
SS Wall Trim securely bonded | / | / |  | /
SS Wall Trim free of gaps between skin and trim | / | / |  | /
If cutouts are present, frames free of router damage | / | / |  | /
If cutouts are present, cutouts meet CAD requirements | / | / |  | /
If required, backers installed, correctly located | / | / |  | /
FAB Final Inspection - Roof
Roof Skin free of surface defects | / | / |  | /
If roof skins are welded, all welds acceptable | / | / |  | /
Roof to Wall Trim free of defects all sides | / | / |  | /
Roof to Wall Trim securely bonded | / | / |  | /
Roof to Wall Trim free of gaps between skin and trim | / | / |  | /
If cutouts are present, frames free of router damage | / | / |  | /
If cutouts are present, cutouts meet CAD requirements | / | / |  | /
Water test completed and passes | / | / |  | /
If required, backers installed, correctly located | / | / |  | /
FAB Final Inspection - Wheel Well Cutouts
Cutouts are symmetrical and fully radiused | / | / |  | /
Cutouts are deburred on inside and outside | / | / |  | /
Cutouts meet CAD requirements | / | / |  | /
Slideout Inspections
Welds are acceptable prior to skin installation | / | / |  | /
Skin bond lines are consistent/acceptable | / | / |  | /
Skins are free of router errors | / | / |  | /
Skins are free of scratches and gouges | / | / |  | /
If cutouts are present, frames free of router damage | / | / |  | /
If cutouts are present, cutouts meet CAD requirements | / | / |  | /
Topside is properly sealed against water intrusion | / | / |  | /
If cutouts are present, cutouts meet CAD requirements | / | / |  | /
Topside is properly sealed against water intrusion | / | / |  | /

## IP Inspection Paint
Project Number: | [PROJECT #] |  | In-Process Inspection PAINT
Project Name: | [PROJECT NAME]
| FAIL (Initial/Date) | Fixed (Initial/Date) | PASS (Initial/Date) | THICKNESS (mils) | Comments
SS Wall Inspection | / | / | /
AFT Wall Inspection | / | / | /
CS Wall Inspection | / | / | /
FWD Wall Inspection | / | / | /
Roof Inspection | / | / | /
Wall: | SS | AFT | CS | FWD | Roof | Comments (required if FAIL)
Dirt/Particulate/Inclusions | o | o | o | o | o
Sags/Runs/ Drips | o | o | o | o | o
Scratches after paint | o | o | o | o | o
Bare Substrate/Voids | o | o | o | o | o
Bulls-eye | o | o | o | o | o
Chips | o | o | o | o | o
Color match with cab <1.0 Delta E | o | o | o | o | o
Consistent gloss | o | o | o | o | o
Cracking or crazing | o | o | o | o | o
Craters, fish-eyes | o | o | o | o | o
Boiling/bubbles/pinholes | o | o | o | o | o
Dings, bumps or dents | o | o | o | o | o
Dry spray/Thin Coating | o | o | o | o | o
Mottle | o | o | o | o | o
Orange Peel | o | o | o | o | o
Overspray | o | o | o | o | o
Peeling | o | o | o | o | o
Ragged mask lines | o | o | o | o | o
Other______________________ | o | o | o | o | o
Other______________________ | o | o | o | o | o

## IP Inspection Assembly
Project Number: | [PROJECT #] |  | In-Process Inspection ASSEMBLY
Project Name: | [PROJECT NAME]
Chassis Inspections | FAIL (Initial/Date) | Fixed (Initial/Date) | Comments (required if FAIL) | PASS (Initial/Date) | Final Comments (as needed)
Fuel and DEF Fill lines are straight and don’t have dips in routing | / | / |  | /
Fuel and DEF Fill vents are positioned above fill line intakes | / | / |  | /
ALL Underchassis Bolts are Torqued and Witness Marked | / | / |  | /
No rusting on Chassis Frame Rail or Nomad FAB Parts along frame | / | / |  | /
No U-Bolts installed over Leaf Springs | / | / |  | /
Cable Runs are routed with protection around sharp corners | / | / |  | /
No kinks are <3" diameter bends in hydraulic lines | / | / |  | /
Undercoating properly applied to exposed surfaces (insulation, flooring, hardware, wheel wells, etc) | / | / |  | /
All fasteners and pass-through points used are properly sealed | / | / |  | /
All hoses/cable runs properly routed and secured to protect from heat/abrasion | / | / |  | /
Ground lights properly mounted - wiring properly protected, secured and dressed | / | / |  | /
Exhaust lines are secure and avoid exhausting near windows and entry doors | / | / |  | /
Axles are properly aligned (trailers or modified axles) | / | / |  | /
| / | / |  | /
INT/EXT Inspections | FAIL (Initial/Date) | Fixed (Initial/Date) | Comments (required if FAIL) | PASS (Initial/Date) | Final Comments (as needed)
Internal 12VDC electrical wiring properly secured, terminated, protected and labeled | / | / |  | /
120VAC electrical conduit and wiring properly installed | / | / |  | /
All interior wiring bundles dressed properly | / | / |  | /
Roof cabling properly routed, secured and protected | / | / |  | /
Interior cabling properly routed, secured and protected | / | / |  | /
Electronics/IT rack cabling properly routed and dressed | / | / |  | /
Flooring properly installed, free of defects, bumps and seams | / | / |  | /
Windows installed correctly and bottom weep holes are unplugged | / | / |  | /
Wall and ceiling insulation properly installed/sprayed if required | / | / |  | /
Proper underhood wiring and terminations | / | / |  | /
ECAB terminations are secured and Blue Anti-Tamper installed correctly | / | / |  | /
In-Process QC Punch List | FAIL (Initial/Date) | Fixed (Initial/Date) | Comments (required if FAIL) | PASS (Initial/Date) | Final Comments (as needed)
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
Ref. CAD Section for Notes if Needed | FAIL (Initial/Date) | Fixed (Initial/Date) | Comments (required if FAIL) | PASS (Initial/Date) | Final Comments (as needed)
Top Level - Overview | / | / |  | /
Section A - Chassis prep, Opening Cutouts & Framing | / | / |  | /
Section B - CSF, CSR, SSF, & SSR - Slideouts | / | / |  | /
Section C - Exterior Underchassis hardware | / | / |  | /
Section D - Exterior Hardware | / | / |  | /
Section E - Flooring and Insulation | / | / |  | /
Section F - Roof Hardware | / | / |  | /
Section G - Framing | / | / |  | /
Section H - AC Electrical | / | / |  | /
Section H06 | / | / |  | /
Section I - DC Electrical | / | / |  | /
Section J - Data, phone, radio & AV cabling and terminations | / | / |  | /
Section K - Plumbing Hardware | / | / |  | /
Section L - Interior wall, ceiling paneling & ceiling mounted hardware | / | / |  | /
Section N - Generator, Fuel & Exhaust Systems | / | / |  | /
Section Q - Internal Work Areas, Cabinetry, & Wall Mounted Hardware | / | / |  | /
| / | / |  | /
| / | / |  | /
| / | / |  | /
Sampling / Surveillance Log | Date | Signature |  | Comments

## Int Equip ID
Project Number: | [PROJECT #] |  | Interior Equipment ID
Project Name: | [PROJECT NAME]
* For multiple items of the same type, write "see additional" in the Comments column then add each item separately in the open cells at the bottom. * All IT equipment IDs are captured by IT Department within separate documentation that is not included within the physical QC binder.
Equipment | Manufacturer | Serial Number | Comments *
Converter 1
Converter 2
Monitor (cab mounted) - (for reverse/turn cameras)
Camera (reverse)
Camera (turn): • Curbside • Streetside
Cab controller (for lights, siren)
(Continue on next page if required)

## Ext Equip ID
Project Number: | [PROJECT #] |  | Exterior Equipment ID
Project Name: | [PROJECT NAME]
* For multiple items of the same type, write "see additional" in the Comments column then add each item separately in the open cells at the bottom. * All IT equipment IDs are captured by IT Department within separate documentation that is not included within the physical QC binder.
Equipment | Manufacturer | Serial Number | Comments *
Pump - Leveling System
Pump - Slideout System
Generator
Fuel tank
Mast
Awning 1
Awning 2
Light Tower
Air Conditioner 1
Air Conditioner 2
Air Conditioner 3
Air Conditioner 4

## Key List
Project Number: | [PROJECT #] |  | Key List
Project Name: | [PROJECT NAME]
* For multiple items of the same type, write "see additional" in the Comments column then add each item separately in the open cells at the bottom.
Compartment/Door | Key Shape & Color | Key Number | Comments *
Underchassis/Shelter Compartments
Entry Door Handle
Entry Door Deadbolt
Internal Cabinets
Internal Drawers
I/O-Passthrough
Fuel Fill
Roll Up
Other Entry
Filing Cabinet
Safe
Refridgerator

## Road Test
Project Number: | [PROJECT #] |  | Road Test
Project Name: | [PROJECT NAME]
Verify The Following (Pre-trip Inspection) | FAIL (Initial/Date) | Fixed (Initial/Date) | Comments (required if FAIL) | PASS (Initial/Date) | Final Comments (as needed)
Perform a walk around inspection for general vehicle condition | / | / |  | /
Confirm all tires have been properly Torqued and Torque Marked (If no mark exists, loosen and re-torque each nut to the required value and apply torque mark). | / | / |  | /
Confirm the Front Axle Track Bar Jam Nuts have been properly Torqued and Torque Marked (If no mark exists, loosen and re-torque each nut to the required value and apply torque mark). | / | / |  | /
LIQUID SPRING AXLE ONLY - Confirm the Front Axle Liquid Spring Nuts have been properly Torqued and Torque Marked according to Manufacturer Spec's (If no mark exists, loosen and re-torque each nut to the required value and apply torque mark). | / | / |  | /
Check and clean mirrors and windshield | / | / |  | /
Check windshield wiper physical condition | / | / |  | /
Check all fluids for correct level | / | / |  | /
Check all belts and hoses for tightness and wear | / | / |  | /
Check under the vehicle for any drips, leaks or other problems | / | / |  | /
Start the engine and let it warm up | / | / |  | /
Check all signal lights and emergency flashers | / | / |  | /
Check all headlight, low and high beam | / | / |  | /
Check internal cab lights | / | / |  | /
Check brakes for functionality forward and backwards | / | / |  | /
Check seat adjustment | / | / |  | /
Check seat belt functionality and warning | / | / |  | /
Check windshield wiper function | / | / |  | /
Check cabin heater and A/C control functionality | / | / |  | /
Check dash dimmer functionality | / | / |  | /
Check radio/stereo functionality | / | / |  | /
Check backup, side, & bird's eye camera functionality | / | / |  | /
Check door locks manually with key | / | / |  | /
Check door locks remotely with fob | / | / |  | /
Check tire pressures are correct and within 2 PSI of OEM Tire Sticker | / | / |  | /
Check all exterior equipment is secured and/or stowed | / | / |  | /
The signature below indicates vehicle/trailer is acceptable and ready to start Road Test: |  |  | Road Test Starting Mileage:
Road Test Start Time:
Signature / Date________________________________ / __________________
Verify The Following (Road Test) | FAIL (Initial/Date) | Fixed (Initial/Date) | Comments (required if FAIL) | PASS (Initial/Date) | Final Comments (as needed)
Drive the following route, unless vehicle size precludes use of this route. Minimum 4 hours or 150 Miles.
Nomad HQ , North on Hwy 2 to MT40, turn left, | / | / |  | /
MT40 to Hwy 93, turn south | / | / |  | /
Hwy 93 to 93 Bypass, turn right | / | / |  | /
93 Bypass to 3 Mile Drive, turn right and head west for 1.1 miles | / | / |  | /
Follow curve to the right to Springcreek Road. | / | / |  | /
In 9/10ths of a mile, continue straight on short gravel road and turn right on 4 Mile drive. | / | / |  | /
Travel east on gravel road for 1.1 miles. Cross Stillwater road and merge right on to 93 Bypass. | / | / |  | /
Exit at 3 Mile drive and repeat loop multiple times for testing. | / | / |  | /
If equiped with manual tank switch, switch tanks between laps. | / | / |  | /
Once rough road test complete, continue further south on 93 Bypass to Hwy 93. Turn south towards Somers. | / | / |  | /
While on US 93, when traffic is clear perform the following tests:
a) Brake test- apply the brakes firmly observe any deviation or pull | / | / |  | /
b) Side to side transition- change lanes firmly without swerving | / | / |  | /
c) Remove both hands from the wheel and observe any deviation in track | / | / |  | /
c1) Try to perform tracking test on a stretch with minimal road crown
d) Slow to 45 and accelerate back to 65. Note any sluggishness | / | / |  | /
Turn Left on MT 82 towards Bigfork, MT 35 | / | / |  | /
Turn Left on MT 35 | / | / |  | /
Turn right on MT 206 and proceed north | / | / |  | /
Turn left on Hwy 2, and proceed west. | / | / |  | /
Turn south at juction of MT 40 and Hwy 2, | / | / |  | /
Proceed south on Hwy 2 to Nomad | / | / |  | /
4-Wheel Drive Test -
Perform the 4WD Test according to the 4WD Route Document | / | / |  | /
POST ROAD TEST INSPECTION:
Confirm all tires and Track Bar Jam nut torque marks have NOT moved/rotated (If a mark has moved/rotated beyond its original marking, clean off the old marking and re-torque each nut to the required value and apply NEW torque mark). | / | / |  | /
Re-torque all wheel lug nuts post road test. (If a mark has moved/rotated SIGNIFICANTLY (more than a 1/4 turn), inform supervisor and QA immediately. If marks moved < 1/4 turn, clean off and re-torque mark. | / | / |  | /
Comments/Observations:
If the vehicle passes all tests, sign below and perform Physical/Operational Tests. |  |  | Road Test Ending Mileage:
Road Test Ending Time:
Sign/Date_____________________________ / __________________

## Alt Route (Libby)
Possible Alternate Route for the Libby area. (2 laps for 149.4 miles.)

## Trailer Road Test
Road Test - Trailer Specific |  |  | Project Number: 803913
Project Name: AL_GAN-REDSTONE_ECTM_01
This checklist is intended as a guide for road testing towable vehicles such as TCT-Tactical Communications Trailers. It does not apply to trailers using Air Brakes, or GVW 26,001 pounds (tow vehicle and trailer combined weight), or a trailer weight of 26,101 pounds or more.
A commercial driver's license (CDL) is a driver's license required in the United States to operate any type of vehicle;
-weighing 26,001 pounds, or 10,001 pounds with any type of trailer towed
-transports quantities of hazardous materials that require warning placards under Department of Transportation (DOT) regulations
-that is designed to transport 16 or more passengers (including driver) or
-more than 8 passengers (including the driver), for compensation.
This includes, but is not limited to, tow trucks, tractor trailers, and buses.
-Interstate drivers of vehicles over 10,001 pounds, but less than 26,001 pounds (not transporting hazmat) need a medical card and Driver Qualification File, but do not need a CDL.
The Commercial Motor Vehicle Safety Act of 1986 was signed into law on October 27, 1986. The primary intent of the Act was to improve highway safety by ensuring that truck drivers and drivers of tractor trailers and buses are qualified to drive Commercial Motor Vehicles (CMVs), and to remove drivers that are unsafe and unqualified from the highways. The Act continued to give states the right to issue CDLs, but the federal government established minimum requirements that must be met when issuing a CDL.
This specific road test can be performed by individuals currently in good standing on Nomad’s Insured Driver List, who are experienced driving the vehicle combination being tested, and have a good sense of how a well-functioning tow vehicle and trailer combination feels and sounds. Those individuals who are in training, but not yet experienced in assessing some of the items on this checklist, must take along a qualified technician.
Road Test Details
Road test date:
Printed Name of Driver:
Description of Tow Vehicle used:
Checklist completed by (Printed Name):
Checklist completed by (Signature):
Starting Mileage (of tow vehicle):
Ending Mileage (of tow vehicle):
Route taken (description or attach map and note any deviations from planned route):
Complete the following checks before leaving Nomad property - Add checkmark to items if acceptable condition is noted. Otherwise, record failures at the bottom of this page and correct before proceeding with the road test.
Confirm that trailer weights are within tow vehicle ratings
Before connecting DOT cord to tow vehicle, confirm that break away batteries have a full charge (required for brakes in case trailer separates from tow vehicle)
Trailer has been prepared for departure and hitched to tow vehicle.
Tow vehicle suspension does not appear overloaded
Trailer running lights operate properly
Trailer signal lights operate properly
Trailer brake lights operate properly
Trailer emergency flashers operate properly
Driver seat adjusted
Tow vehicle mirrors adjusted
Both sides of trailer are visible in tow vehicle mirrors
Parking brake released
Verify trailer brakes operate correctly when manually engaged (via brake controller in tow vehicle & attempt to drive forward slowly)
Verify trailer brakes operate correctly when activated by tow vehicle brakes (drive forward slowly & depress tow vehicle brake pedal)
Verify trailer breakaway switch operates correctly (pull breakaway switch cable on trailer & attempt to drive forward slowly)
Re-insert breakaway switch cable
Post a spotter behind the trailer
Slowly drive in reverse while steering sharply in one direction, keeping a close eye on the trailer's front corners approaching the tow vehicle. Confirm that a 70° turn does not cause trailer to contact any part of tow vehicle.
Drive forward to straighten trailer, then repeat above step in other direction.
Verify clearance height is posted in driver's view, in feet and inches. During road test, observe bridge and other structure clearances to ensure that trailer will fit.
Record below, any failures from the above list and note how they were corrected before conducting full road test.
Road Test Observations
Tow vehicle stability:
Acceleration:
Braking:
Steering:
Cornering:
Cruising:
Sway:
Tracking:
Effects of large trucks passing:
Effects of wind gusts:
Project specific notes - Repeat function testing of outriggers, mast, and generator and record results:
Comments/Observations:
If the vehicle passes all tests, sign below and perform Physical/Operational Tests.
Sign/Date_____________________________ / __________________

## Water Test
Project Number: |  | [PROJECT #] |  |  | Water Test
Project Name: |  | [PROJECT NAME]
Exterior | Location (F,CS,SS,R) | FAIL (Initial/Date) | Fixed (Initial/Date) | Comments (required if FAIL) | PASS (Initial/Date) | Final Comments (as needed)
Entry Door 1 |  | / | / |  | /
Entry Door 2 |  | / | / |  | /
Entry Door 3 |  | / | / |  | /
Entry Door 4 |  | / | / |  | /
Compartment Door 1 |  | / | / |  | /
Compartment Door 2 |  | / | / |  | /
Compartment Door 3 |  | / | / |  | /
Compartment Door 4 |  | / | / |  | /
Compartment Door 5 |  | / | / |  | /
Compartment Door 6 |  | / | / |  | /
Compartment Door 7 |  | / | / |  | /
Compartment Door 8 |  | / | / |  | /
Compartment Door 9 |  | / | / |  | /
Compartment Door 10 |  | / | / |  | /
Slide out 1 |  | / | / |  | /
Slide out 2 |  | / | / |  | /
Slide out 3 |  | / | / |  | /
Slide out 4 |  | / | / |  | /
Window 1 |  | / | / |  | /
Window 2 |  | / | / |  | /
Window 3 |  | / | / |  | /
Window 4 |  | / | / |  | /
Window 5 |  | / | / |  | /
Window 6 |  | / | / |  | /
AC Unit(s) |  | / | / |  | /
Fan(s)/Vent(s) |  | / | / |  | /
Antenna(s) |  | / | / |  | /
Pass through(s) |  | / | / |  | /
Cable Gland(s) |  | / | / |  | /
Use open cells below to add key components that require water test documentation
|  | / | / |  | /
|  | / | / |  | /
|  | / | / |  | /
Comments/Observations:
If the vehicle passes all tests, sign below.
Sign/Date_____________________________ / __________________

## Operational
Project Number: | [PROJECT #] |  |  |  | Physical-Operational Testing
Project Name: | [PROJECT NAME]
The goal of the "Physical Operational Tests" is to do a full start-up and shut-down of the main systems to ensure both functionality as well as to complete physical inspections of each main component. This test differs from the Final QC Test in that the Final Test will go into much deeper detail of the cosmetics of the build (ie. paint, countertops, carpeted wall panels, etc.). Similarly, the Physical Operational Tests differ from the Quantitative Tests as those require the collection of data to verify proper functions. Whereas the Physical Operational Test will simply verify that the mast goes up and down, the Quantitative Test will document that it does a full cycle in less than "X" minutes and thus either meets a PASS or FAIL.
Main Category | Test Notes | Test | FAIL (Initial/Date) | Fixed (Initial/Date) | Comments (required if FAIL) | PASS (Initial/Date) | Final Comments (as needed)
Entry steps/stairs | • Smoothly and fully deploys and stows • Easily latches and locks without excessive force | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Entry doors | • Smoothly and fully deploys and stows • Easily latches and locks without excessive force | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Compartment doors (External) | • Smoothly and fully deploys and stows • Easily latches and locks without excessive force | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Cabinet doors (Internal) | • Smoothly and fully deploys and stows • Easily latches and locks without excessive force | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Generator |  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Shore Power | • Installed and Sealed appropriately • Shore Cord easily connects and secures in place | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Inverter(s) |  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Converter(s) |  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
AC digital meter |  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
DC digital meter |  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
DOT Lights - marker | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
DOT Lights - stop/tail/turn | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
DOT Lights - reverse | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Scene Lights - curbside | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Scene Lights - rear | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Scene Lights - streetside | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Scene Lights - front | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Emergency Lights (large flashers) - curbside | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Emergency Lights (large flashers) - rear | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Emergency Lights (large flashers) - streetside | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Emergency Lights (large flashers) - front | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Emergency Lights (small flashers) - curbside | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Emergency Lights (small flashers) - rear | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Emergency Lights (small flashers) - streetside | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Emergency Lights (small flashers) - front | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Emergency Lights (roof beacons) - all | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Ground Lights (all) | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Compartment Lights & Switches - curbside | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Compartment Lights & Switches - streetside | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Emergency Lights (light bar) - over cab | • Operates as expected when activated • No Damage to housings | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Leveling System | • Smoothly and fully extends and retracts • Fully closes when retract is complete without damaging nearby equipment | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Slideout Room (SS - rear): | • Smoothly and fully extends and retracts • "Flush" floors when extended (< +/- 1/8") | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Slideout Room (CS - rear): | • Smoothly and fully extends and retracts • "Flush" floors when extended (< +/- 1/8") | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Slideout Room (SS - fwd): | • Smoothly and fully extends and retracts • "Flush" floors when extended (< +/- 1/8") | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Slideout Room (CS - fwd): | • Smoothly and fully extends and retracts • "Flush" floors when extended (< +/- 1/8") | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Awning 1 | • Smoothly and fully extends and retracts • Fully closes when retract is complete | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Awning 2 | • Smoothly and fully extends and retracts • Fully closes when retract is complete | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Awning 3 | • Smoothly and fully extends and retracts • Fully closes when retract is complete | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Awning 4 | • Smoothly and fully extends and retracts • Fully closes when retract is complete | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Vertical Mast 1 | • Smoothly and fully extends and retracts • Fully closes when retract is complete without damaging nearby equipment | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Vertical Mast 2 | • Smoothly and fully extends and retracts • Fully closes when retract is complete without damaging nearby equipment | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Light Tower | • Smoothly and fully extends and retracts • Fully closes when retract is complete without damaging nearby equipment | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Weather Station |  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Lifts (ADA, tool) | • Smoothly and fully extends and retracts • Fully closes when retract is complete without damaging nearby equipment | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Emergency Siren |  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Overhead Main Light(s) |  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Overhead Colored Light(s) |  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
HVAC 1 |  | Physical Inspection | / | / |  | /
HVAC (cool) |  | Functional Tests | / | / |  | /
HVAC (heat) |  | Functional Tests | / | / |  | /
HVAC (fan) |  | Functional Tests | / | / |  | /
HVAC 2 |  | Physical Inspection | / | / |  | /
HVAC (cool) |  | Functional Tests | / | / |  | /
HVAC (heat) |  | Functional Tests | / | / |  | /
HVAC (fan) |  | Functional Tests | / | / |  | /
HVAC 3 |  | Physical Inspection | / | / |  | /
HVAC (cool) |  | Functional Tests | / | / |  | /
HVAC (heat) |  | Functional Tests | / | / |  | /
HVAC (fan) |  | Functional Tests | / | / |  | /
HVAC 4 |  | Physical Inspection | / | / |  | /
HVAC (cool) |  | Functional Tests | / | / |  | /
HVAC (heat) |  | Functional Tests | / | / |  | /
HVAC (fan) |  | Functional Tests | / | / |  | /
Heater 1 |  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Heater 2 |  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Heater 3 |  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Heater 4 |  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Roof fan/vent(s) |  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Refrigerator(s) |  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Microwave | • ON when Powered Up • OFF when Powered Down | Physical Inspection | / | / |  | /
|  | Powers up | / | / |  | /
Coffee Maker | • ON when Powered Up • OFF when Powered Down | Physical Inspection | / | / |  | /
|  | Powers up | / | / |  | /
Folding/Removable Tables/Counters |  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Main ceiling lts & switch (group 1): | • ON when switch actuated • OFF when switch actuated | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Main ceiling lts & switch (group 2): | • ON when switch actuated • OFF when switch actuated | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Main ceiling lts & switch (group 3): | • ON when switch actuated • OFF when switch actuated | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Main ceiling lts & switch (group 4): | • ON when switch actuated • OFF when switch actuated | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Ceiling "red" lts & switch (group 1): | • ON when switch actuated • OFF when switch actuated | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Ceiling "red" lts & switch (group 2): | • ON when switch actuated • OFF when switch actuated | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Ceiling "red" lts & switch (group 3): | • ON when switch actuated • OFF when switch actuated | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Workstations #1 task lts & switch(es): | • ON when switch actuated • OFF when switch actuated | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Workstations #2 task lts & switch(es): | • ON when switch actuated • OFF when switch actuated | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Workstations #3 task lts & switch(es): | • ON when switch actuated • OFF when switch actuated | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Workstations #4 task lts & switch(es): | • ON when switch actuated • OFF when switch actuated | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
"Always-On" Courtesy lts & switch: | • All ON if AC power lost to vehicle • All ON when main entry limit switch tripped • All OFF after 15 minutes of main entry door closed | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Slideout lts & switch (SS-rear): | • ON when switch actuated • OFF when switch actuated | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Slideout lts & switch (CS-rear): | • ON when switch actuated • OFF when switch actuated | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Slideout lts & switch (SS-fwd): | • ON when switch actuated • OFF when switch actuated | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Slideout lts & switch (CS-fwd): | • ON when switch actuated • OFF when switch actuated | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Interlocks: | • Power source according to CAD • Correct overrides | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Bumper Swing Arm: | •Smooth operation over full range of motion •Latch properly engages (Open Position) •Pin is easy to insert (Closed Position) | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Exterior Monitor Box: | •Mechanical Function (Door, Latch, Keyboard tray) •Electrical (Compartment Light, Power Outlets) | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Super Single Conversion: | •Rear Wheel Clearance (No air bag pressure) •Front Wheel Clearance (Lock-to-lock steering) •Smooth Operation of Front Suspension •4x4 Engagement and Operation | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
|  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
|  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
|  | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /

## Quantitative
Project Number: |  |  | [PROJECT #] |  | Quantitative Testing
Project Name: |  |  | [PROJECT NAME]
• The goal of the "Quantitative Tests" is to capture numerical values to determine PASS or FAIL for critical components where a basic functions test may not provide sufficient evidence that the equipment is properly functioning. This test data will also be important for future warranty claims, as well as service and troubleshooting in that it will document numerical baseline data of the vehicle's as-built design prior to shipping to the end user. • This test differs from the Physical Operational Tests (which go through a complete start-up and shut-down procedure to check basic "on/off" functionality of all components) and the Final QC Tests (which focus on the overall cosmetics).
Syst. | Main Category | Test Notes | Expected Data | Measured Data | FAIL (Initial/Date) | Fixed (Initial/Date) | Comments (required if FAIL) | PASS (Initial/Date) | Final Comments (as needed)
Leveling | Auto level | Operate using OEM Provided Control Interface. | Level on 2 planes @ interior countertop <= 3 minutes. 4 legs in contact with ground. | min:sec = | / | / |  | /
| Auto Retract |  | All legs fully retracted <= 2 minutes. | min:sec = | / | / |  | /
Digital Multimeter (Blue Sea/EKM) | AC Voltage | Blue Sea or EKM Meter. If no meter present, CONSULT ENGINEERING. | L1 +/- 6V vs. handheld multimeter | L1 meter (V) = L1 handheld (V) = Voltage difference = | / | / |  | /
|  |  | L2 +/- 6V vs. handheld multimeter | L2 meter (V) = L2 handheld (V) = Voltage difference = | / | / |  | /
|  |  | L1-L2 +/- 12V vs. handheld multimeter | L1-L2 meter (V) = L1-L2 handheld (V) = Voltage difference = | / | / |  | /
| AC Frequency |  | L1 +/- 0.5Hz vs. handheld multimeter | L1 meter (Hz) = L1 handheld (Hz) = Frequency difference = | / | / |  | /
|  |  | L2 +/- 0.5Hz vs. handheld multimeter | L2 meter (Hz) = L2 handheld (Hz) = Frequency difference = | / | / |  | /
| AC Amperage |  | L1 +/- 5% vs. handheld multimeter | L1 meter (A) = L1 handheld (A) = % different = | / | / |  | /
|  |  | L2 +/- 5% vs. handheld multimeter | L2 meter (A) = L2 handheld (A) = % different = | / | / |  | /
| DC Voltage |  | +/- 3% vs. handheld multimeter | L1 meter (VDC) = L1 handheld (VDC) = % different = | / | / |  | /
| DC Amperage |  | +/- 3% vs. handheld multimeter | L1 meter (A) = L1 handheld (A) = % different = | / | / |  | /
Generator | Voltage | Measured with multimeter. Ensure multimeter is documented on the last page of this Quantitative section. | L1-G: 114-126 volts | L1-G (volts) = | / | / |  | /
|  |  | L1-N: 114-126 volts | L1-N (volts) = | / | / |  | /
|  |  | L2-G: 114-126 volts | L2-G (volts) = | / | / |  | /
|  |  | L2-N: 114-126 volts | L2-N (volts) = | / | / |  | /
|  |  | G-N: <0.5 volts | G-N (volts) = | / | / |  | /
|  |  | L1-L2: 228-252 volts | L1-L2 (volts) = | / | / |  | /
| Frequency |  | L1 = 59-61 Hz | L1 (Hz) = | / | / |  | /
|  |  | L2 = 59-61 Hz | L2 (Hz) = | / | / |  | /
| Power Output (full load) | Ensure NO errors present during or after testing. | Run at full load (100% rating) for 30 minutes without any issues (error codes) on generator. | ERROR or NO ERROR (circle one) | / | / |  | /
| Generator Sound | Location 1 to be at head height (sitting) at workstation group 1. | Workstations 1: dB to be <65 | WS 1 (dB) = | / | / |  | /
|  | Location 2 to be at head height (sitting) at workstation group 2. | Workstations 2: dB to be <65 | WS 2 (dB) = | / | / |  | /
|  | Location 3 to be at head height (sitting) at workstation group 3. | Workstations 3: dB to be <65 | WS 3 (dB) = | / | / |  | /
|  | Location 4 to be at head height (sitting) at workstation group 4. | Workstations 4: dB to be <65 | WS 4 (dB) = | / | / |  | /
|  | Location to be at head height (sitting) at conference table. | Conference Table: dB to be <65 | Conf (dB) = | / | / |  | /
| Remote start/stop panel | Location to be at head height (sitting) at conference table. | Hour meter to accurately show total generator runtime. | Hour meter accurate to within 0.1 hours of actual after running for exactly 2.0 hours continuously | / | / |  | /
| Generator Intake Temp | Measure temperature of both the Ambient Air and the Intake Air on the Generator after 30 minutes of Run Time. The air measured at the intake should be less than 15F. | Generator (temp ∆ <15°F) | °F(intake) = °F(ambient) = ∆°F = | / | / |  | /
Shore Power | Voltage | Measured at the load panel to ensure no major wiring issues between shore input and panel. | L1-G: 100-130 volts. | L1-G (volts) = | / | / |  | /
|  |  | L1-N: 100-130 volts. | L1-N (volts) = | / | / |  | /
|  |  | L2-G: 100-130 volts. | L2-G (volts) = | / | / |  | /
|  |  | L2-N: 100-130 volts. | L2-N (volts) = | / | / |  | /
|  |  | G-N: <0.5 volts | G-N (volts) = | / | / |  | /
|  | Note that Nomad's facility has 3-phase, thus has 208V across the 2 poles. | L1-L2: 180-230 volts (for Nomad's facility) | L1-L2 (volts) = | / | / |  | /
120VAC Receptacles | Circuit 1 Circuit Breaker = | Using tool that verifies that Hot, Neutral and Ground are properly wired to outlet. | Proper wiring | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  | Voltage measured at actual wall outlet - pick any within that respective circuit. | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 2 Circuit Breaker = | See Above. | Proper wiring + GFI trips | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 3 Circuit Breaker = | See Above. | Proper wiring | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 4 Circuit Breaker = | See Above. | Proper wiring | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 5 Circuit Breaker = | See Above. | Proper wiring | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 6 Circuit Breaker = | See Above. | Proper wiring | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 7 Circuit Breaker = | See Above. | Proper wiring | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 8 Circuit Breaker = | See Above. | Proper wiring | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 9 Circuit Breaker = | See Above. | Proper wiring | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 10 Circuit Breaker = | See Above. | Proper wiring | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 11 Circuit Breaker = | See Above. | Proper wiring | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 12 Circuit Breaker = | See Above. | Proper wiring | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 13 Circuit Breaker = | See Above. | Proper wiring | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 14 Circuit Breaker = | See Above. | Proper wiring | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 15 Circuit Breaker = | See Above. | Proper wiring | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 16 Circuit Breaker = | See Above. | Proper wiring + GFI trips | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 17 Circuit Breaker = | See Above. | Proper wiring + GFI trips | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 18 Circuit Breaker = | See Above. | Proper wiring + GFI trips | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 19 Circuit Breaker = | See Above. | Proper wiring + GFI trips | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 20 Circuit Breaker = | See Above. | Proper wiring + GFI trips | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 21 Circuit Breaker = | See Above. | Proper wiring + GFI trips | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 22 Circuit Breaker = | See Above. | Proper wiring + GFI trips | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 23 Circuit Breaker = | See Above. | Proper wiring + GFI trips | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 24 Circuit Breaker = | See Above. | Proper wiring + GFI trips | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 25 Circuit Breaker = | See Above. | Proper wiring + GFI trips | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 26 Circuit Breaker = | See Above. | Proper wiring + GFI trips | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 27 Circuit Breaker = | See Above. | Proper wiring + GFI trips | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 28 Circuit Breaker = | See Above. | Proper wiring + GFI trips | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 29 Circuit Breaker = | See Above. | Proper wiring + GFI trips | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
| Circuit 30 Circuit Breaker = _____ | See Above. | Proper wiring + GFI trips | YES / NO / Spare / Blank / NA (circle one) | / | / |  | /
|  |  | Voltage 100-130 volts | Volts = | / | / |  | /
Heating | Wall Heaters | Heating (amp draw) | HTR1 (amps <18A) | Amps = | / | / |  | /
|  |  | HTR2 (amps <18A) | Amps = | / | / |  | /
|  |  | HTR3 (amps <18A) | Amps = | / | / |  | /
|  |  | HTR4 (amps <18A) | Amps = | / | / |  | /
|  | Heating (air temp) | HTR1 (temp ∆ >20°F) | °F(room) = °F(outlet) = ∆°F = | / | / |  | /
|  |  | HTR2 (temp ∆ >20°F) | °F(room) = °F(outlet) = ∆°F = | / | / |  | /
|  |  | HTR3 (temp ∆ >20°F) | °F(room) = °F(outlet) = ∆°F = | / | / |  | /
|  |  | HTR4 (temp ∆ >20°F) | °F(room) = °F(outlet) = ∆°F = | / | / |  | /
Lighting | Light intensity | Measure at counter level roughly where keyboard would be. | Workstations 1: > 215Lux | Lux = | / | / |  | /
|  |  | Workstations 2: > 215Lux | Lux = | / | / |  | /
|  |  | Workstations 3: > 215Lux | Lux = | / | / |  | /
|  |  | Workstations 4: > 215Lux | Lux = | / | / |  | /
|  |  | Conference Table: > 215Lux | Lux = | / | / |  | /
HVAC (Rooftop) | Cooling (air temp) COOL + Fan HIGH (TOTAL ROOM TEMP ∆) | Temp difference measured between intake air and output air. | AC#1 (temp ∆ >16°F) | °F(intake) = °F(outlet) = ∆°F = | / | / |  | /
|  |  | AC#2 (temp ∆ >16°F) | °F(intake) = °F(outlet) = ∆°F = | / | / |  | /
|  |  | AC#3 (temp ∆ >16°F) | °F(intake) = °F(outlet) = ∆°F = | / | / |  | /
|  |  | AC#4 (temp ∆ >16°F) | °F(intake) = °F(outlet) = ∆°F = | / | / |  | /
| Airflow (Fan HIGH) | Measure airflow directly in middle of both the forward and rearward air outputs for each AC unit. Meter to be ~1" off from grille. | AC#1 (FPS >20 - both sides) | Fwd (FPS)= Rearwd (FPS) = | / | / |  | /
|  |  | AC#2 (FPS >20 - both sides) | Fwd (FPS)= Rearwd (FPS) = | / | / |  | /
|  |  | AC#3 (FPS >20 - both sides) | Fwd (FPS)= Rearwd (FPS) = | / | / |  | /
|  |  | AC#4 (FPS >20 - both sides) | Fwd (FPS)= Rearwd (FPS) = | / | / |  | /
| Cooling (amp draw) COOL + Fan HIGH | 120VAC amperage gathered within AC load panel with AC clamp meter for each HVAC circuit. | AC#1 (amps <16A @ ext. <95°F) | Amps = | / | / |  | /
|  |  | AC#2 (amps <16A @ ext. <95°F) | Amps = | / | / |  | /
|  |  | AC#3 (amps <16A @ ext. <95°F) | Amps = | / | / |  | /
|  |  | AC#4 (amps <16A @ ext. <95°F) | Amps = | / | / |  | /
| Heating (amp draw) HEAT + Fan HIGH | 120VAC amperage gathered within AC load panel with AC clamp meter for each HVAC circuit. | AC#1 (amps <18A) | Amps = | / | / |  | /
|  |  | AC#2 (amps <18A) | Amps = | / | / |  | /
|  |  | AC#3 (amps <18A) | Amps = | / | / |  | /
|  |  | AC#4 (amps <18A) | Amps = | / | / |  | /
| Heating (heat strips) HEAT + Fan HIGH (TOTAL ROOM TEMP ∆) | Temp difference measured between intake air and output air. | AC#1 (temp ∆ >10°F) | °F(intake) = °F(outlet) = ∆°F = | / | / |  | /
|  |  | AC#2 (temp ∆ >10°F) | °F(intake) = °F(outlet) = ∆°F = | / | / |  | /
|  |  | AC#3 (temp ∆ >10°F) | °F(intake) = °F(outlet) = ∆°F = | / | / |  | /
|  |  | AC#4 (temp ∆ >10°F) | °F(intake) = °F(outlet) = ∆°F = | / | / |  | /
| HVAC Sound | Take measurement at head level directly below center of ceiling shroud for each AC unit. | AC#1 (dB <70dB) | dB = | / | / |  | /
|  |  | AC#2 (dB <70dB) | dB = | / | / |  | /
|  |  | AC#3 (dB <70dB) | dB = | / | / |  | /
|  |  | AC#4 (dB <70dB) | dB = | / | / |  | /
HVAC (Sidemount) | Cooling (air temp) COOL + Fan HIGH (TOTAL ROOM TEMP ∆) | Temp difference measured between intake air and output air. | AC#1: • temp ∆ >18°F for 2-ton (20k btu) • temp ∆ >24°F for 3-ton (30k btu) | °F(intake) = °F(outlet) = ∆°F = | / | / |  | /
|  |  | AC#2: • temp ∆ >18°F for 2-ton (20k btu) • temp ∆ >24°F for 3-ton (30k btu) | °F(intake) = °F(outlet) = ∆°F = | / | / |  | /
| Airflow (Fan HIGH) | Measure airflow directly in middle of both the forward and rearward air outputs for each AC unit. Meter to be ~1" off from grille. | AC#1 (FPS >20 - center out grille) | FPS = | / | / |  | /
|  |  | AC#2 (FPS >20 - center out grille) | FPS = | / | / |  | /
| Cooling (amp draw) COOL + Fan HIGH | 120VAC amperage gathered within AC load panel with AC clamp meter for each HVAC circuit. | AC#1: • amps <20A @ ext. <95°F for each hot leg for 2-ton (20k btu) • amps <45A @ ext. <95°F for each hot leg for 3-ton (30k btu) | Amps = | / | / |  | /
|  |  | AC#2: • amps <20A @ ext. <95°F for each hot leg for 2-ton (20k btu) • amps <45A @ ext. <95°F for each hot leg for 3-ton (30k btu) | Amps = | / | / |  | /
| Heating (amp draw) HEAT + Fan HIGH | 120VAC amperage gathered within AC load panel with AC clamp meter for each HVAC circuit. | AC#1: • amps <20A each leg (4kw) • amps <50A each leg (10kw) | Amps = | / | / |  | /
|  |  | AC#2: • amps <20A each leg (4kw) • amps <50A each leg (10kw) | Amps = | / | / |  | /
| Heating (heat strips) HEAT + Fan HIGH (TOTAL ROOM TEMP ∆) | Temp difference measured between intake air and output air. | AC#1: • temp ∆ >70°F (4kw) • temp ∆ >110°F (10kw) | °F(intake) = °F(outlet) = ∆°F = | / | / |  | /
|  |  | AC#2: • temp ∆ >70°F (4kw) • temp ∆ >110°F (10kw) | °F(intake) = °F(outlet) = ∆°F = | / | / |  | /
| HVAC Sound | Take measurement at head level directly below center of ceiling shroud for each AC unit. | AC#1 (dB <70dB) | dB = | / | / |  | /
|  |  | AC#2 (dB <70dB) | dB = | / | / |  | /
PTO | Voltage |  | L1-G: 114-126 volts | L1-G (volts) = | / | / |  | /
|  |  | L1-N: 114-126 volts | L1-N (volts) = | / | / |  | /
|  |  | L2-G: 114-126 volts | L2-G (volts) = | / | / |  | /
|  |  | L2-N: 114-126 volts | L2-N (volts) = | / | / |  | /
|  |  | G-N: <0.5 volts | G-N (volts) = | / | / |  | /
|  |  | L1-L2: 228-252 volts | L1-L2 (volts) = | / | / |  | /
| Frequency |  | L1 = 59-61 Hz | L1 (Hz) = | / | / |  | /
|  |  | L2 = 59-61 Hz | L2 (Hz) = | / | / |  | /
| Power Output (full load) |  | Run at full load (100% rating) for 30 minutes without any issues (error codes) on generator. | ERROR or NO ERROR (circle one) | / | / |  | /
| PTO Sound | Location 1 to be at head height (sitting) at workstation group 1. | Workstations 1: dB to be <65 | WS 1 (dB) = | / | / |  | /
|  | Location 2 to be at head height (sitting) at workstation group 2. | Workstations 2: dB to be <65 | WS 2 (dB) = | / | / |  | /
|  | Location 3 to be at head height (sitting) at workstation group 3. | Workstations 3: dB to be <65 | WS 3 (dB) = | / | / |  | /
|  | Location 4 to be at head height (sitting) at workstation group 4. | Workstations 4: dB to be <65 | WS 4 (dB) = | / | / |  | /
|  | Location to be at head height (sitting) at conference table. | Conference Table: dB to be <65 | Conf (dB) = | / | / |  | /
Max Sound | Combined Sound (Generator operating at full load and HVAC system operating on HIGH. | Take measurement at head level directly below center of ceiling shroud for each AC unit. | CS Front (dB<80dB) | dB = | / | / |  | /
|  |  | SS Front (dB<80dB) | dB = | / | / |  | /
|  |  | CS Rear (dB<80dB) | dB = | / | / |  | /
|  |  | SS Rear (dB<80dB) | dB = | / | / |  | /
Grounding | Location 1 (truck chassis - shelter subframe) |  | <20 milliohms. | Milliohms = | / | / |  | /
| Location 2 (shelter subframe - birdcage framing) |  | <20 milliohms. | Milliohms = | / | / |  | /
| Location 3 (ground stud - subframe) |  | <10 milliohms. | Milliohms = | / | / |  | /
Mechanical | Wheel Lug Nuts | Ensure all Lug Nuts are properly torqued to values listed in Form 310, or OEM Chassis defined specifications. This test MUST occur PRIOR to the Road Test. | Each Lug Nut MUST be Torqued and IMMEDIATELY Torque Marked to ensure proper Lug Nut Torquing. Units in Ft*Lbs | SSF = CSF = SSR = CSR = | / | / |  | /
| CS-SS physical balance | Park on level surface. Measure ground to skirt, just behind the rear wheel. | Ground to CS/SS skirt verticals to be < 1.0 in difference (just behind rear wheel) | SS = CS = ∆(in) = | / | / |  | /
| Fuel gauge (analog) | Fuel Gauge Indicator Functionality | Fuel gauge and sending unit (SU) both work correctly. | Fuel gauge shows: - FULL when sending unit (SU) float at top. - half full when SU float at middle. - EMPTY when SU float at bottom. | / | / |  | /
| Exhaust does NOT discharge near entry doors/windows | Make sure exhaust doesn’t discharge near doors or windows | Away from Doors and Windows | PASS / FAIL | / | / |  | /
| Exhaust Extends PAST Shelter | Measure extended distance from Shelter to End of Exhaust | Past External Shelter | inches = | / | / |  | /
Lift & Lay | Lift & Lay 1 | Deploy and Stow Functionality Testing. | Time to full UP: < 1 minute | Time (min:sec): | / | / |  | /
|  |  | Time to full DOWN: < 1 minute | Time (min:sec): | / | / |  | /
| Lift & Lay 2 | Deploy and Stow Functionality Testing. | Time to full UP: < 1 minute | Time (min:sec): | / | / |  | /
|  |  | Time to full DOWN: < 1 minute | Time (min:sec): | / | / |  | /
Mast(s) | Vertical mast 1 | NOTE: For Pneumatic Masts: Time to pump shutting off after mast fully extended: < 2 minutes. | Time to full UP: (small) < 3 minutes | Time (min:sec): | / | / |  | /
|  |  | Time to full UP: (medium) < 4 minutes | Time (min:sec): | / | / |  | /
|  |  | Time to full UP: (large) < 5 minutes | Time (min:sec): | / | / |  | /
|  |  | Time to full DOWN: (small) < 2 minutes | Time (min:sec): | / | / |  | /
|  |  | Time to full DOWN: (medium) < 3 minutes | Time (min:sec): | / | / |  | /
|  |  | Time to full DOWN: (large) < 4 minutes | Time (min:sec): | / | / |  | /
| Vertical mast 2 | NOTE: For Pneumatic Masts: Time to pump shutting off after mast fully extended: < 2 minutes. | Time to full UP: (small) < 3 minutes | Time (min:sec): | / | / |  | /
|  |  | Time to full UP: (medium) < 4 minutes | Time (min:sec): | / | / |  | /
|  |  | Time to full UP: (large) < 5 minutes | Time (min:sec): | / | / |  | /
|  |  | Time to full DOWN: (small) < 2 minutes | Time (min:sec): | / | / |  | /
|  |  | Time to full DOWN: (medium) < 3 minutes | Time (min:sec): | / | / |  | /
|  |  | Time to full DOWN: (large) < 4 minutes | Time (min:sec): | / | / |  | /
Solar | Battery Charging | Vehicle OFF and 12V ON | Deplete Battery for at least 30 minutes and check Solar Charging Functionality on Solar OEM Interface. Measure Current from Solar output to Battery Input (4 - 6A) | Amps = | / | / |  | /
| Inverter |  | Check Inverter Backed Outlets are Functional | PASS / FAIL | / | / |  | /
48VDC-12VDC | Converter 1 (500) |  | 500W | Watt rating = | / | / |  | /
| Converter 2 (500) |  | 500W | Watt rating = | / | / |  | /
| Converter 3 (500) |  | 500W | Watt rating = | / | / |  | /
| Converter 4 (500) |  | 500W | Watt rating = | / | / |  | /
| Converter 1 (start-up) |  | Voltage: 13.1V - 13.9V | Volts = | / | / |  | /
| Converter 2 (start-up) |  | Voltage: 13.1V - 13.9V | Volts = | / | / |  | /
| Converter 3 (start-up) |  | Voltage: 13.1V - 13.9V | Volts = | / | / |  | /
| Converter 4 (start-up) |  | Voltage: 13.1V - 13.9V | Volts = | / | / |  | /
| System draw (all on) |  | Amps < 150 | Amps = YES / NO | / | / |  | /
| System voltage (all on) |  | Volts between 13.1V - 13.79V | Volts = | / | / |  | /
| Converter 1 @ 35 minutes |  | Voltage: 13.5V - 13.9V | Volts = | / | / |  | /
| Converter 2 @ 35 minutes |  | Voltage: 13.5V - 13.9V | Volts = | / | / |  | /
| Converter 1 (42A) |  | Amps 1 - 42 | Amps = YES / NO | / | / |  | /
| Converter 2 (42A) |  | Amps 1 - 42 | Amps = YES / NO | / | / |  | /
| Converter 3 (42A) |  | Amps 1 - 42 | Amps = YES / NO | / | / |  | /
| Converter 4 (42A) |  | Amps 1 - 42 | Amps = YES / NO | / | / |  | /
| Battery Charger (auto) |  | Converters charging when shore power plugged in | YES / NO (circle one) | / | / |  | /
|  |  | Converters charging when AC power is on | YES / NO (circle one) | / | / |  | /
Neverdown | Bank 1 |  | Powers On with 46-58.5V output | Voltage: | / | / |  | /
| Bank 2 |  | Powers On with 46-58.5V output | Voltage: | / | / |  | /
| 51V bus |  | 51V Bus with 46-58.5V on it | Voltage: | / | / |  | /
| AC-DC Charge circuit |  | Increase of at least 0.1V after 60 minutes of inlet power or PTO with no loads | Voltage Start: Time: Voltage End: Time: | / | / |  | /
| Inverters |  | Combined AC Loads up to 20kW for minimum 1 hour without failure | Voltage Start: Time: Load: Voltage End: Time: Load: | / | / |  | /
| Intermotive |  | Passes all 7 tests on intermotive manual page 14, with test 3 activated by jumpering R2 on NTC1 | PASS / FAIL | / | / |  | /
| Auto start test (1/3) |  | Prime PTO and reset NTC, load system with 12-20kW for minimum 2 hours without interference, discharging from above 55% and monitor autostart below 20% | PASS / FAIL | / | / |  | /
| Generator auto start (2/3) |  | Disconnect load, charge above 20%, reconnect load but do not prime PTO, discharge system below 20% in a normally active state, verify generator starts automatically, charging occurs | PASS / FAIL | / | / |  | /
| Auto stop test (3/3) |  | Charge above 20%, reconnect load and prime PTO, reset NTC, then discharge. Allow PTO to auto start triggered by NTC and charge to auto shutoff triggered by NTC without interference | PASS / FAIL | / | / |  | /
Converter(s) | Converter 1 (spec) |  | (varies per model) | Amp rating = | / | / |  | /
| Converter 2 (spec) |  | (varies per model) | Amp rating = | / | / |  | /
| Converter 1 (start-up) |  | Voltage: 14.4V - 14.8V | Volts = | / | / |  | /
| Converter 2 (start-up) |  | Voltage: 14.4V - 14.8V | Volts = | / | / |  | /
| System draw (all on) | Assuming that Blue Sea/EKM DMM passed at the start of this test, should be able to use this panel itself for capturing this and other amp readings below. | Amps < sum of converters | Amps = YES / NO | / | / |  | /
| System voltage (all on) | Power all 12VDC on. Take voltage when current is relatively steady (not when initial motor start-up, etc.) | Volts between 13.1V - 14.7V | Volts = | / | / |  | /
| Converter 1 @ 35 minutes |  | Voltage: 13.5V - 13.9V | Volts = | / | / |  | /
| Converter 2 @ 35 minutes |  | Voltage: 13.5V - 13.9V | Volts = | / | / |  | /
| Converter 1 (draw) |  | Amps < rating | Amps = YES / NO | / | / |  | /
| Converter 2 (draw) |  | Amps < rating | Amps = YES / NO | / | / |  | /
| Battery Charger (auto) |  | Converter's 120VAC outlet powered when 15A shore cord plugged into ext. inlet | YES / NO (circle one) | / | / |  | /
|  |  | Converter's 120VAC outlet not powered when 15A shore cord unplugged from ext. inlet | YES / NO (circle one) | / | / |  | /
Misc. 12VDC Electrical | Slideout Room 1 (out) |  | Amp increases 50-110A | Amp increase = Voltage = | / | / |  | /
| Slideout Room 1 (in) |  | Amp increases 50-110A | Amp increase = Voltage = | / | / |  | /
| Slideout Room 1 (out) |  | Time to full OUT: < 45 seconds | Time (min:sec): | / | / |  | /
| Slideout Room 1 (in) |  | Time to full IN: < 45 seconds | Time (min:sec): | / | / |  | /
| Slideout Room 2 (out) |  | Amp increases 50-110A | Amp increase = Voltage = | / | / |  | /
| Slideout Room 2 (in) |  | Amp increases 50-110A | Amp increase = Voltage = | / | / |  | /
| Slideout Room 2 (out) |  | Time to full OUT: < 45 seconds | Time (min:sec): | / | / |  | /
| Slideout Room 2 (in) |  | Time to full IN: < 45 seconds | Time (min:sec): | / | / |  | /
| Slideout Room 3 (out) |  | Amp increases 50-110A | Amp increase = Voltage = | / | / |  | /
| Slideout Room 3 (in) |  | Amp increases 50-110A | Amp increase = Voltage = | / | / |  | /
| Slideout Room 3 (out) |  | Time to full OUT: < 45 seconds | Time (min:sec): | / | / |  | /
| Slideout Room 3 (in) |  | Time to full IN: < 45 seconds | Time (min:sec): | / | / |  | /
| Slideout Room 4 (out) |  | Amp increases 50-110A | Amp increase = Voltage = | / | / |  | /
| Slideout Room 4 (in) |  | Amp increases 50-110A | Amp increase = Voltage = | / | / |  | /
| Slideout Room 4 (out) |  | Time to full OUT: < 45 seconds | Time (min:sec): | / | / |  | /
| Slideout Room 4 (in) |  | Time to full IN: < 45 seconds | Time (min:sec): | / | / |  | /
| Leveling Legs (leveling) |  | Amp increases 60-80A under no load (traveling in air) | Amp increase = | / | / |  | /
|  |  | Amp increases no more than 150A when under load. | Amp max increase = | / | / |  | /
|  |  | Voltage stays between 11.2V and 15.5V during full cycle. | Voltage (lowest) = Voltage (highest) = | / | / |  | /
| Leveling Legs (retracting) |  | Amp increases 60-80A under no load (traveling in air) | Amp increase = | / | / |  | /
|  |  | Amp increases no more than 150A when under load. | Amp max increase = | / | / |  | /
|  |  | Voltage stays between 11.2V and 15.5V during full cycle. | Voltage (lowest) = Voltage (highest) = | / | / |  | /
| Inverter |  | Discuss with Electrical Engineering on expectations | PASS / FAIL | / | / |  | /
ADA Lift | ADA Lift Electrical | Verify Electrical Properties. | Amp increases no more than 70A when under load. | Amp increase = | / | / |  | /
| ADA Lift Light Status | Verify Lift Operation Enabled if and only if A OR B conditions are met: | A 1. Ignition AND 2. Park Brake Set AND 3. Enable Switch On | PASS / FAIL PB, SL, Park, WC Steady on | / | / |  | /
|  |  | B 1. Lift Door Open AND 2. Park Brake Set AND 3. Enable Switch | PASS / FAIL PB, SL, Park, WC Steady on , Door Open Flashing | / | / |  | /
|  | Verify Parking brake locked out and Lift operational once condition A is met: | A 1. Ignition AND 2. Park Brake Set AND 3. Enable Switch On | PASS / FAIL Lift Fully Operational, PB Locked out PB, SL, Park, WC Steady on , Door Open Flashing | / | / |  | /
|  | Verify Parking brake locked out and lift operational once condition B is met: | B 1. Lift Door Open AND 2. Park Brake Set AND 3. Enable Switch | PASS / FAIL Lift Fully Operational, PB Locked out PB, SL, Park, WC Steady on , Door Open Flashing | / | / |  | /
|  | Verify Lift operation inhibited when condition A OR B is NOT met: | A 1. Ignition AND 2. Park Brake Set AND 3. Enable Switch On | PASS / FAIL Enable switch off, lift disabled No Lights | / | / |  | /
|  |  | B 1. Lift Door Open AND 2. Park Brake Set AND 3. Enable Switch | PASS / FAIL Park Brake disengaged, lift disabled No Lights | / | / |  | /
|  | Verify Parking Brake can be disengaged once conditions C have been met: | C 1. Lift Door Closed AND 2. Enable Switch OFF | PASS / FAIL No Lights | / | / |  | /
NTC | NTC (AC electrical) | Automatic Transfer Switch (ATS) Functionality Testing. | When in AUTO setting on rotary switch: Automatically switches to SHORE power when shore power is available. | Function properly ( YES / NO ) | / | / |  | /
|  |  | When in AUTO setting on rotary switch: Automatically switches to GEN power when generator is running and shore power is disconnected. | Function properly ( YES / NO ) | / | / |  | /
|  |  | When in GEN setting on rotary switch: Switches to GEN power input only. | Function properly ( YES / NO ) | / | / |  | /
|  |  | When in SHORE setting on rotary switch: Switches to SHORE power input only. | Function properly ( YES / NO ) | / | / |  | /
| Tablet properly displays: | NTC Controlled Tablet displays the following information. | AC electrical information - values on tablet are within following tolerances versus what is measured with multimeter: - AC voltage (+/- 5V) - AC frequency (+/- 1Hz) | Volts: NTC ______ DMM _______ Diff ______V Freq: NTC ______ DMM _______ Diff ______Hz | / | / |  | /
|  |  | DC electrical information - values on tablet are within following tolerances versus what is measured with multimeter: - DC voltage (+/- 0.5V) - DC amperage (+/- 10%) | Volts: NTC ______ DMM _______ Diff ______V Amps: NTC ______ DMM _______ Diff ______% | / | / |  | /
|  |  | Fuel tank information: - fuel level status (empty - full) | All levels are accurate ( YES / NO ) | / | / |  | /
| Tablet properly controls: | NTC Controlled Tablet properly controls the following information. | • Deployment Wizard | All systems function properly ( YES / NO ) | / | / |  | /
|  |  | • Stow Wizard | All systems function properly ( YES / NO ) | / | / |  | /
|  |  | • Generator start and stop | All systems function properly ( YES / NO ) | / | / |  | /
|  |  | • Selection for incoming AC power (shore, generator and auto) | All systems function properly ( YES / NO ) | / | / |  | /
|  |  | • vertical mast - extend and retract | All systems function properly ( YES / NO ) | / | / |  | /
|  |  | • VSAT antenna - deploy and stow | All systems function properly ( YES / NO ) | / | / |  | /
Plumbing | Tank heater (fresh) | Physical Inspection. | Pad on tank heats up. |  | / | / | Do not activate heater without water in tank!! | /
| Tank heater (black) |  | Pad on tank heats up. |  | / | / | Do not activate heater without water in tank!! | /
| Pipe heaters (fresh) |  | Sleeves on pipes heat up. |  | / | / | Do not activate heater without water in tank!! | /
| Pipe heaters (black) |  | Sleeves on pipes heat up. |  | / | / | Do not activate heater without water in tank!! | /
| Tank sensors (fresh) | Tank Info Panel properly displays the following information. | Level panel illuminates: - Empty - 3 gallons - 1/3 full - 7 gallons - 2/3 full - 14 gallons - Full - 20 gallons |  | / | / |  | /
| Tank sensors (black) |  | Level panel illuminates: - Empty - 3 gallons - 1/3 full - 10 gallons - 2/3 full - 20 gallons - Full - 30 gallons |  | / | / |  | /
| Water Heater 1 | Water temperature increases as each faucet. If Power Restrictions require Water Heater Management, see the test intruction below. | Water temperature increases at least 40F | Water temp (cold) = Water temp (hot) = Water temp increase = Hot Water Management: Timer Relay Setting Value (IF REQ'D) = | / | / |  | /
| Water Heater 2 |  | Water temperature increases at least 40F | Water temp (cold) = Water temp (hot) = Water temp increase = Hot Water Management: Timer Relay Setting Value (IF REQ'D) = | / | / |  | /
| Water Heater 3 |  | Water temperature increases at least 40F | Water temp (cold) = Water temp (hot) = Water temp increase = Hot Water Management: Timer Relay Setting Value (IF REQ'D) = | / | / |  | /
| Water Heater 4 |  | Water temperature increases at least 40F | Water temp (cold) = Water temp (hot) = Water temp increase = Hot Water Management: Timer Relay Setting Value (IF REQ'D) = | / | / |  | /
| Water Heater Management Test |  | Hot Water Management Test Instructions: 1. Set up the temperature sensor at a sink location to measure the initial water temperature. 2. Press the ‘water heater enable’ switch at sink location, record the time when the switch was pressed. 3. Imediately turn on the Hot Water. 4. Observe the temperature increase of the water at each sink location and record the time taken to reach the desired temperature rise. 5. Report test data to engineering, adjust the timer relay settings accordingly and repeat the testing procedure.
Test Tooling Used:
Description |  |  |  | Model | ID # | Exp. Date (Cal.) |  | Additional Notes
AC/DC clamp multimeter | [7 empty] | (used to test for AC and DC volts and amps; AC frequency)
Temperature meter (°F)
Anemometer (FPS)
Sound meter (dB)
Milliohm meter (mΩ)
Receptacle tester | [7 empty] | (used to test for proper wiring of hot/neutral/ground and GFI tripping)
Light meter (lux)
Note on D25: Shane Ackerly: Location 1 to be at head height (sitting) at workstation group 1.
Note on D26: Shane Ackerly: Location 2 to be at head height (sitting) at workstation group 2.
Note on D27: Shane Ackerly: Location 3 to be at head height (sitting) at workstation group 3.
Note on D28: Shane Ackerly: Location 4 to be at head height (sitting) at workstation group 4.
Note on D29: Shane Ackerly: Location to be at head height (sitting) at conference table.
Note on D30: Shane Ackerly: Location to be at head height (sitting) at conference table.
Note on B32: Shane Ackerly: measured at the load panel to ensure no major wiring issues between shore input and panel.
Note on D37: Shane Ackerly: Note that Nomad's facility has 3-phase, thus has 208V across the 2 poles.
Note on D38: Shane Ackerly: using tool that verifies that Hot, Neutral and Ground are properly wired to outlet
Note on D39: Shane Ackerly: Voltage measured at actual wall outlet - pick any within that respective circuit
Note on D106: Shane Ackerly: Measure at counter level roughly where keyboard would be.
Note on B111: Shane Ackerly: Temp difference measured between intake air and output air.
Note on B115: Shane Ackerly: Measure airflow directly in middle of both the forward and rearward air outputs for each AC ceiling unit. Meter to be ~1" off from grille.
Note on B119: Shane Ackerly: 120VAC amperage gathered within AC load panel with AC clamp meter for each HVAC circuit.
Note on B123: Shane Ackerly: 120VAC amperage gathered within AC load panel with AC clamp meter for each HVAC circuit.
Note on B127: Shane Ackerly: Temp difference measured between intake air and output air.
Note on B131: Shane Ackerly: Take measurement at head level directly below center of ceiling shroud for each AC unit.
Note on B135: Shane Ackerly: Temp difference measured between intake air and output air.
Note on B137: Shane Ackerly: Measure airflow directly in middle of both the forward and rearward air outputs for each AC ceiling unit. Meter to be ~1" off from grille.
Note on B139: Shane Ackerly: 120VAC amperage gathered within AC load panel with AC clamp meter for each HVAC circuit.
Note on B141: Shane Ackerly: 120VAC amperage gathered within AC load panel with AC clamp meter for each HVAC circuit.
Note on B143: Shane Ackerly: Temp difference measured between intake air and output air.
Note on B145: Shane Ackerly: Take measurement at head level directly below center of ceiling shroud for each AC unit.
Note on D156: Shane Ackerly: Location 1 to be at head height (sitting) at workstation group 1.
Note on D157: Shane Ackerly: Location 2 to be at head height (sitting) at workstation group 2.
Note on D158: Shane Ackerly: Location 3 to be at head height (sitting) at workstation group 3.
Note on D159: Shane Ackerly: Location 4 to be at head height (sitting) at workstation group 4.
Note on D160: Shane Ackerly: Location to be at head height (sitting) at conference table.
Note on B169: Brian Putnam: Park on level surface. Measure ground to skirt, just behind the rear wheel.
Note on B222: Shane Ackerly: Assuming that Blue Sea DMM passed at the start of this test, should be able to use this panel itself for capturing this and other amp readings below.
Note on B223: Shane Ackerly: Assuming that Blue Sea DMM passed at the start of this test, should be able to use this panel itself for capturing this and other amp readings below. Power all 12VDC on. Take voltage when current is relatively steady (not when initial motor start-up, etc.)

## Parasitic Drain
Project Number: | [PROJECT #] |  |  |  | Parasitic Drain Test
Project Name: | [PROJECT NAME]
Min Drain (Amps): 0 |  |  | Typical Drain (Amps): 0.02 |  |  | Max Drain (Amps): 0.05
Circuit Measured | Initial Parasitic Drain (Amps) | Final Parasitic Drain (Amps) | FAIL (Initial/Date) | Fixed (Initial/Date) | Comments (required if FAIL) | PASS (Initial/Date) | Final Comments (as needed)
Chassis As Received |  |  | / | / |  | /
Shelter |  |  | / | / |  | /
Chassis And Shelter |  |  | / | / |  | /
Date : |  |  |  |  | Battery Model :
Time : |  |  |  |  | Battery Group/Size :
Project Number: |  |  |  |  | Battery RC Rating :
Project Name: |  |  |  |  | Nomad p/n :
Elec. Drawing/Rev :
Tested By : |  |  |  |  | Disconnect SW p/n :
Test Date:
Battery Type: |  |  |  |  | Meter Manf :
Battery Ref on Dwg : |  |  |  |  | Meter Model :
Battery Manf : |  |  |  |  | Amps Full Scale :

## IT Equipment
Project Number: |  | [PROJECT #] | IT Equipment Test
Project Name: |  | [PROJECT NAME]
System | Main Category | Test | FAIL (Initials + Date) | Fixed (Initials + Date) | Comments (required if FAIL) | PASS (initials + date) | Final Comments (as needed) | SWI
Rack and Infrastructure | PDUs | Power tests | / | / |  | /
| Temperature Module | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| Rack 1 Fan | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| Electronics Rack | Physical Inspection | / | / |  | /
| Panduit Patch Panels | Physical Inspection | / | / |  | /
| Panduit Wall plates | Physical Inspection | / | / |  | /
| Cat6 Cabling | Physical Inspection/Dressing | / | / |  | /
| Rack 1 STACO UPS | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| Rack 1 Bipass Switch | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
System | Main Category | Test | FAIL (Initials + Date) | Fixed (Initials + Date) | Comments (required if FAIL) | PASS (initials + date) | Final Comments (as needed) | SWI
Satellite | VSAT Antenna | Physical Inspection | / | / |  | /
|  | Compass | / | / |  | /
|  | GPS | / | / |  | /
|  | Modem communication | / | / |  | /
|  | Reference satellite acquisition | / | / |  | /
|  | Data satellite acquisition | / | / |  | /
| BUC | Physical Inspection | / | / |  | /
| PLL LNB | Physical Inspection | / | / |  | /
| Cabling | Physical Inspection/Dressing | / | / |  | /
| VSAT Modem | Physical Inspection | / | / |  | /
|  | Network Connectivity | / | / |  | /
| DSTV Antenna | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
System | Main Category | Test | FAIL (Initials + Date) | Fixed (Initials + Date) | Comments (required if FAIL) | PASS (initials + date) | Final Comments (as needed) | SWI
Data | Cisco 4331 Router | Physical Inspection | / | / |  | /
|  | Wired Internet/Intranet Connectivity | / | / |  | /
|  | Wireless Internet/Intranet Connectivity | / | / |  | /
| Cisco 2960X Switch | Physical Inspection | / | / |  | /
|  | Network Connectivity | / | / |  | /
| Cisco WAP121-k9 | Physical Inspection | / | / |  | /
|  | Wireless Internet/Intranet Connectivity | / | / |  | /
System | Main Category | Test | FAIL (Initials + Date) | Fixed (Initials + Date) | Comments (required if FAIL) | PASS (initials + date) | Final Comments (as needed) | SWI
Voice | Cisco 4331 Router | Physical Inspection | / | / |  | /
|  | Wired phone registration | / | / |  | /
|  | Wireless phone registration | / | / |  | /
|  | Conference phone registration | / | / |  | /
|  | Workstation SIP inbound/outbound | / | / |  | /
|  | Conference SIP inbound/outbound | / | / |  | /
|  | Telular Voice inbound/outbound | / | / |  | /
|  | Telular Fax inbound/outbound | / | / |  | /
|  | Iridium inbound/outbound | / | / |  | /
| Call Manager Express | Proper call routing | / | / |  | /
| Cisco Unity Express | Voicemail setup | / | / |  | /
| Cisco 7945G Deskphone | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| Cisco WiFi 8822G Portable Phone | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| Conference Phone | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| Cell Booster (Make, model) | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
System | Main Category | Test | FAIL (Initials + Date) | Fixed (Initials + Date) | Comments (required if FAIL) | PASS (initials + date) | Final Comments (as needed) | SWI
Audio/Video | AV Matrix (Crestron, Extron, KVM, Etc.) | Physical Inspection | / | / |  | /
|  | Remote control IR functional tests | / | / |  | /
|  | Proper source/zone control | / | / |  | /
| Remote Keypads | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| AV Matrix control Processor | Physical Inspection | / | / |  | /
|  | Proper source/zone control | / | / |  | /
| TV #1 (make, model, size) | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| TV #2 (make, model, size) | Physical Inspection | / | / |  | /
|  | Linked to TV speakers | / | / |  | /
| DirecTV D12 | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
|  | Service Activation | / | / |  | /
| HDMI Port | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
System | Main Category | Test | FAIL (Initials + Date) | Fixed (Initials + Date) | Comments (required if FAIL) | PASS (initials + date) | Final Comments (as needed) | SWI
Radios | Motorola APX Radio | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| Motorola XTL Radio | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| Micom Radio | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| Icom Radio | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| Kenwood Radio | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| Interoperability Device | Physical Inspection | / | / |  | /
|  | ACU-1000 controller software | / | / |  | /
|  | PCNXU software radio | / | / |  | /
| RF Repeater | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| External Whip Antennas | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| Radio Chargers | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
System | Main Category | Test | FAIL (Initials + Date) | Fixed (Initials + Date) | Comments (required if FAIL) | PASS (initials + date) | Final Comments (as needed) | SWI
VTC | Camera | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| Mic | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| Speakers | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| Cabling | Physical Inspection/Dressing | / | / |  | /
System | Main Category | Test | FAIL (Initials + Date) | Fixed (Initials + Date) | Comments (required if FAIL) | PASS (initials + date) | Final Comments (as needed) | SWI
Printer | HP Laserjet P4014dm | Physical Inspection | / | / |  | /
|  | Print Test | / | / |  | /
| Cabling | Physical Inspection/Dressing | / | / |  | /
| HP Color Laser Jet CM3530fx | Physical Inspection | / | / |  | /
|  | Print Test | / | / |  | /
System | Main Category | Test | FAIL (Initials + Date) | Fixed (Initials + Date) | Comments (required if FAIL) | PASS (initials + date) | Final Comments (as needed) | SWI
Power | UPS | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
| Bypass Switch | Physical Inspection | / | / |  | /
|  | Functional Tests | / | / |  | /
Note on I3: Shane Ackerly: SWI for referencing how to complete each item (how to inspect, what is a PASS or FAIL, etc.)
Note on I17: Shane Ackerly: SWI for referencing how to complete each item (how to inspect, what is a PASS or FAIL, etc.)
Note on I31: Shane Ackerly: SWI for referencing how to complete each item (how to inspect, what is a PASS or FAIL, etc.)
Note on I39: Shane Ackerly: SWI for referencing how to complete each item (how to inspect, what is a PASS or FAIL, etc.)
Note on I59: Shane Ackerly: SWI for referencing how to complete each item (how to inspect, what is a PASS or FAIL, etc.)
Note on I76: Shane Ackerly: SWI for referencing how to complete each item (how to inspect, what is a PASS or FAIL, etc.)
Note on I96: Shane Ackerly: SWI for referencing how to complete each item (how to inspect, what is a PASS or FAIL, etc.)
Note on I104: Shane Ackerly: SWI for referencing how to complete each item (how to inspect, what is a PASS or FAIL, etc.)
Note on I110: Shane Ackerly: SWI for referencing how to complete each item (how to inspect, what is a PASS or FAIL, etc.)

## Final QC
Project Number: |  | [PROJECT #] |  | Final QC
Project Name: |  | [PROJECT NAME]
Verify The Following |  | FAIL (Initial/Date) | Fixed (Initial/Date) | Comments (required if FAIL) | PASS (Initial/Date) | Final Comments (as needed)
CAB | ALL OEM keys/fobs work correctly (Entry, Ignition, Fuel - 2 Sets Min.) | / | / |  | /
| Cab is clean | / | / |  | /
| Cab console finish is even consistent, and defect free | / | / |  | /
| Cab equipment and wiring properly (inlcuding Fire Extinguisher, if applicable) is mounted, terminated and labeled | / | / |  | /
| Information placards properly secured (i.e. PN 406514 or PN 408340) | / | / |  | /
| NO "Check Engine" or similar OEM Codes present | / | / |  | /
| Record Odometer Reading at time of inspection |  |  | Mileage:______________________ | /
| Reverse, Side, & Birdseye cameras operate properly | / | / |  | /
| Leveling system "Retract All" switch operates correctly | / | / |  | /
| Running Boards installed and functioning properly (if applicable) | / | / |  | /
| Door Interlocks functioning properly/Code system reads correctly | / | / |  | /
| Windshield is clean (inside and out) | / | / |  | /
UNDER CHASSIS | Under Chassis U-Bolts are properly torqued. | / | / |  | /
| Under chassis undercoating properly applied per specs | / | / |  | /
| Leveling system hydraulic hoses properly run, secured, protected & dressed | / | / |  | /
| All mechanical fasteners and pass-through points used are properly sealed | / | / |  | /
| All hoses/cable runs properly routed and secured to protect from heat/abrasion | / | / |  | /
| Fuel fill ports properly installed, grounded, and vented | / | / |  | /
| Ground lights properly mounted - wiring properly protected, secured and dressed | / | / |  | /
EXTERIOR | Tires and wheels are free from defects | / | / |  | /
| Wheel Lug Nuts are properly torqued. | / | / |  | /
| Axles are properly aligned (applicable to trailers or modified axles) | / | / |  | /
| Exterior paint is to spec, free of defects and all panels color match | / | / |  | /
| All exterior surfaces free of dings, dents and other discontinuities. | / | / |  | /
| Graphics are installed to spec | / | / |  | /
| Trailer receiver tow sticker applied | / | / |  | /
| Windows properly installed and sealed. Bottom weep holes are unplugged | / | / |  | /
| Steps properly installed (Check all functionality) | / | / |  | /
| Entrance doors properly installed - no binding or gaps in seals | / | / |  | /
| Spare tire properly mounted on vehicle | / | / |  | /
| Reflective Tape installed to door edging (if required) | / | / |  | /
| Mast equipment properly installed | / | / |  | /
| Mast deploys and retracts properly | / | / |  | /
| Reverse and side cameras properly mounted | / | / |  | /
| Shore power inlet(s) properly mounted | / | / |  | /
| Entrance door grab handles properly mounted and straight | / | / |  | /
| I/O patch panel properly terminated and finished | / | / |  | /
| Exterior speaker installed and function properly | / | / |  | /
| External surveillance cameras installed and function properly | / | / |  | /
| D.O.T. wiring and lights properly secured, terminated and protected | / | / |  | /
| Scene lights and wiring properly secured, terminated and protected | / | / |  | /
| Emergency lighting and wiring properly secured, terminated and protected | / | / |  | /
| External GFCI outlets mounted and operate properly | / | / |  | /
GENERATOR | Fuel tank, fill, gauge and hoses properly installed and plumbed to generator | / | / |  | /
| Generator box properly sealed and soundproofed | / | / |  | /
| Generator mounting surface properly prepped and painted | / | / |  | /
| Generator properly installed | / | / |  | /
| Generator exhaust system properly installed | / | / |  | /
| Hour meter accurately shows total generator run time (within 0.1 hours) | / | / |  | /
| Generator Run Time is >2hrs (Ref. Quant. Testing) | / | / | Run Time:______________________ | /
COMPARTMENT BOXES | All compartments are clean | / | / |  | /
| Battery system/wiring properly secured, terminated, protected and labeled | / | / |  | /
| External 12VDC electrical wiring properly secured, terminated, protected & labeled | / | / |  | /
| Equipment mounted inside compartment boxes completed/installed | / | / |  | /
| Compartment boxes and doors properly installed - no binding or gaps in seals | / | / |  | /
| Compartment door lights and motion switches operating properly | / | / |  | /
| Compartment doors all keyed alike. Key mechanisms function properly | / | / |  | /
ROOF | Data satellite antenna properly mounted and sealed | / | / |  | /
| All other roof-mounted antennas properly mounted and sealed | / | / |  | /
| HVAC properly mounted | / | / |  | /
| Radio rails properly mounted and sealed | / | / |  | /
| Roof cabling properly routed, secured and protected | / | / |  | /
| Awning mounted properly | / | / |  | /
| Awning deploys and retracts properly | / | / |  | /
INTERIOR | Interior is clean (panels, counters, floors, data racks, etc.) | / | / |  | /
| Painted surfaces free of defects/flaws | / | / |  | /
| Electrical distribution center panels and gauges properly secured and finished | / | / |  | /
| 12VDC load panel properly dressed, terminated and labeled | / | / |  | /
| 12VDC switch panels and wiring properly mounted, terminated and labeled | / | / |  | /
| 120VAC electrical conduit and wiring properly installed and torqued | / | / |  | /
| 120VAC load panel properly wired and labeled | / | / |  | /
| All interior wiring bundles dressed properly | / | / |  | /
| Computers/monitors/TVs properly mounted/secured | / | / |  | /
| Wiring for controllers/monitors/TVs properly secured, terminated and labeled | / | / |  | /
| Wall outlets and wiring properly mounted, terminated, labeled and function properly | / | / |  | /
| Overhead lighting and wiring properly secured, terminated and protected | / | / |  | /
| No damage to light housings, ends, lenses | / | / |  | /
| 120VAC electrical receptacles are straight and tight with no gapping | / | / |  | /
| Shore cord installed and functions properly | / | / |  | /
| Electronics/IT rack(s) properly mounted and grounded | / | / |  | /
| Electronics properly mounted and terminated in rack | / | / |  | /
| Electronics/IT rack cabling properly routed and dressed | / | / |  | /
| A/V and data/phone ports properly terminated and labeled throughout vehicle | / | / |  | /
| All internal HVAC vents properly secured and functional (HEAT/COOL/AUTO) | / | / |  | /
| Safety detectors properly installed (smoke, CO, LP) | / | / |  | /
| Finish trim properly installed and cleaned | / | / |  | /
| Entrance door trim and threshold properly installed and cleaned | / | / |  | /
| Deadbolts and locks properly engage/disengage | / | / |  | /
| Flooring properly installed, cleaned, free of defects, bumps and seams | / | / |  | /
| Wall and ceiling panels properly installed | / | / |  | /
| Panels flush at all panel-to-panel joints with no gaps | / | / |  | /
| Panels secured properly/consistently | / | / |  | /
| Fastener heads recessed into carpet with no debris around screw head | / | / |  | /
| Lines in carpet pattern parallel with edges (wall lines horizontal to floor) | / | / |  | /
| Lines in flooring pattern parallel with all vehicle flooring (including slideouts, if applicable) | / | / |  | /
| Cosmetic - no runs, tears, burns in walls, ceiling or flooring | / | / |  | /
| Countertops properly installed and free of defects (top surfaces and edge molding) | / | / |  | /
| Bottom surfaces of countertops properly painted with no defects or missing paint) | / | / |  | /
| Galley appliances installed and operating properly | / | / |  | /
| Cabinets properly installed with no gaps | / | / |  | /
| Wall equipment properly mounted (phones, clocks, fire extinguishers, dry erase, etc.) | / | / |  | /
| Productivity equipment properly mounted/secured (printer, copier, etc.) | / | / |  | /
Final Function Re-Checks | Proper function - all components via manual controls | / | / |  | /
| Proper function - all components via NTC main moduals | / | / |  | /
| Proper function - all components via NTC wizard moduals | / | / |  | /
| Start Up Shut Down Procedure completed with no errors | / | / |  | /
| Start Up Shut Down Procedure aligns with NTC wizards | / | / |  | /
| Inspect IT Build/Test Docs Complete | / | / |  | /
| Inspect NTC Build/Test Docs Complete | / | / |  | /
MISC. | Cranks/handles are installed & secured - 1 per Hydraulic Tank & 2 Sets per Slide out (1 set of 2 Short Bolts & 1 set of 2 Long Bolts (awning, slide outs, leveling system, etc.) | / | / |  | /
| Two complete key sets. All keys and locks function properly | / | / |  | /
| All weights are measured, recorded and within specs | / | / |  | /
| Project ID Plate has been ordered (PN 401826) | / | / |  | /
| NOMAD Badges applied (if NOT contractually restricted) | / | / |  | /
| Team Leads have completed inspection of the MH carts | / | / |  | /
Add Additional Comments/Findings Below:
|  | / | / |  | /
|  | / | / |  | /
|  | / | / |  | /
|  | / | / |  | /
|  | / | / |  | /
|  | / | / |  | /
|  | / | / |  | /
|  | / | / |  | /